## Overview
NexaMart M2 — Group Execution Tracker
Milestone | M2 of 2 — Validate, Fix, Analyse, Conclude
Submission | Single ZIP: nexamart_m2_group_[N].zip
Campaign window | 8-28 Aug 2024 (baseline 1 Mar-31 Jul; ramp 1-7 Aug; post 29 Aug-14 Sep)
Repo / branch | github.com/ARIF-rb/nexamart-m2 — working branch: main
Deadline | Day 10 EOD
PROGRESS
Anomalies resolved
KPI views done
Validation checks passing
Deliverables done
Tasks done

## _lists (hidden)
Not started | Pending | No | Lead
In progress | Pass | Yes | M2
Blocked | Fail |  | M3
Done |  |  | M4
M5
M6

## Anomalies
ID | Cat | Title | Owner | Source Silver | Resolution method / b_class | Detection | Resolved | Gold rebuilt | Re-verified->0 | Status | Notes
A1 | A | Cancelled EC order still in revenue | M5 | silver_ec_orders | Zero cancelled revenue | No | No | No | No | Not started
A2 | A | Payment captured after cancellation | M5 | silver_pg_transactions | Flag reversal-required | No | No | No | No | Not started
A3 | A | Tax/shipping inclusion mismatch | M5 | silver_ec_orders; silver_pos_transactions | Normalise to tax-exclusive | No | No | No | No | Not started
A4 | A | NexaLocal seller-marked-sold as confirmed revenue | M6 | silver_nl_listing_events | Relabel ESTIMATED (feeds B6) | No | No | No | No | Not started
A5 | A | Website ATP>0 while warehouse physical=0 | Lead | silver_wh_inventory_snapshots | Correct ATP to 0 | No | No | No | No | Not started
A6 | A | Negative ATP / sellable qty | M4 | silver_si_inventory_snapshots | Correct to 0 + oversell flag | No | No | No | No | Not started
A7 | A | Returned stock sellable before inspection | Lead | silver_rr_return_receipts | Zero pre-inspection restock | No | No | No | No | Not started
A8 | A | Missing snapshot days (1-7 Aug ramp-up) | Lead | silver_si_inventory_snapshots | Reconstruct -> RECONSTRUCTED/INFERRED | No | No | No | No | Not started
A9 | A | Same SKU -> different products | M3 | silver_product_master | Canonical product (catalogue wins) | No | No | No | No | Not started
A10 | A | Open-box restocked as NEW | M4 | silver_rr_return_receipts | Correct condition to open-box | No | No | No | No | Not started
A11 | A | Placeholder customer 9999 collision | M2 | silver_customer_master; silver_ec_orders | Rekey guests to GUEST-{session} | No | No | No | No | Not started
A12 | A | Listing marked sold then relisted | Lead | silver_nl_listings | Link + exclude from GMV; reliability=LOW | No | No | No | No | Not started
A13 | A | Coordinated fake listing ring | M6 | silver_nl_listings | Flag risk tier; exclude | No | No | No | No | Not started
A14 | A | Delivered before shipped | Lead | silver_dc_delivery_events | +36h median; >72h manual review | No | No | No | No | Not started
A15 | A | Review before delivery | M6 | silver_rv_reviews | verified_purchase=FALSE | No | No | No | No | Not started
A16 | A | Duplicate complaint cases | M6 | silver_cs_cases | Dedupe to canonical case key | No | No | No | No | Not started
B1 | B | Campaign-window attribution | Lead | silver_ec_orders; silver_ws_sessions | Attribute (b_class=ATTRIBUTED, conf 0.85) | No | No | No | No | Not started
B2 | B | Partial refund period attribution | Lead | silver_rr_refund_events | Recognise in return period | No | No | No | No | Not started
B3 | B | Inventory movement without ref order | Lead | silver_wh_inventory_movements | Classify PROBABLE_MISSING_REF (INFERRED) | No | No | No | No | Not started
B4 | B | NexaLocal listing -> catalogue match | M3 | silver_nl_listings | Match >=0.75 / 0.65-0.75 review / <0.65 unmatched | No | No | No | No | Not started
B5 | B | Cross-channel identity resolution | M2 | silver_customer_master | Probabilistic merge >=0.90 | No | No | No | No | Not started
B6 | B | Estimated Classified GMV model | M2 | silver_nl_listing_events | Weighted signals + -/+35% band, ESTIMATED | No | No | No | No | Not started
B7 | B | BOPIS Completed without pickup event | Lead | silver_ec_orders; silver_dc_delivery_events | Treat as fulfilled; collection_unconfirmed | No | No | No | No | Not started
B8 | B | Seller trust composite score | M2 | silver_ts_sellers | Weighted composite -> 5 risk tiers | No | No | No | No | Not started

## Tasks
Member | Day | Task# | Title | Est hrs | Blocked by | Status | Notes
Lead | 0 | 1 | Create NEXAMART_MARTS + confirm M1 Gold | 0.5 |  | Not started
Lead | 1 | 2 | Run 9:30 kickoff; assign anomaly owners | 1.5 |  | Not started
Lead | 1 | 3 | Detection SQL for your anomalies | 3 |  | Not started
Lead | 2 | 4 | Capture before-counts + scope/impact | 2 |  | Not started
Lead | 3 | 5 | A5 (ATP→0), A7 (zero pre-inspection restock) | 2.5 |  | Not started
Lead | 3 | 6 | A8 snapshot reconstruction (1–7 Aug, stores 3/7/12) | 3 |  | Not started
Lead | 3 | 7 | A14 delivery-clock fix (+36h; >72h escalate) | 2 |  | Not started
Lead | 4 | 8 | B1 attribution (102 orders), B2 refund period, B3 null-ref, B7 BOPIS | 4 |  | Not started
Lead | 4 | 9 | Write corrected Silver back + idempotency asserts | 2 |  | Not started
Lead | 5 | 10 | Rebuild your facts (fulfilment, inventory txn, store snapshot, classified snapshot, clickstream, complaint) | 4 | member dim rebuilds (M3 dim_product, M2 dim_customer) where your facts join them | Not started
Lead | 6 | 11 | Orchestrate the 10-check suite; own checks 1,2,5,7,10 | 3 |  | Not started
Lead | 7 | 12 | Build your 3 views + review all 28 for certainty/segregation | 3 |  | Not started
Lead | 8 | 13 | GSV→NCR waterfall + 7-team reconciliation narrative | 4 |  | Not started
Lead | 9 | 14 | Write Exec summary + S5 Conclusion; assemble all members' sections | 4 |  | Not started
Lead | 10 | 15 | Export PDF; build submission ZIP; final checks | 2 |  | Not started
M2 | 1 | 1 | Detection SQL for A11, B5, B6, B8 | 3 |  | Not started
M2 | 2 | 2 | Confirm A11 collision (Sarah Chen) + lock B6 formula + B8 weights | 2 |  | Not started
M2 | 3 | 3 | A11 rekey guests to GUEST-{session} | 2.5 |  | Not started
M2 | 4 | 4 | B5 identity merge (≥0.90), B6 estimated GMV, B8 trust tiers | 5 | Lead A12 relisting links (exclude relisted originals from B6 GMV) | Not started
M2 | 4 | 5 | Write corrected silver_customer_master + silver_ts_sellers; idempotency asserts | 1.5 |  | Not started
M2 | 5 | 6 | Rebuild dim_customer (SCD2) + identity bridge, dim_seller_risk_tier, seller-perf fact | 3.5 |  | Not started
M2 | 6 | 7 | Own checks 6 + 9 (certainty completeness + segregation) | 1.5 |  | Not started
M2 | 7 | 8 | Build your 8 NexaLocal/seller + GMV views | 4 |  | Not started
M2 | 8 | 9 | NexaLocal & Seller Quality page | 3 |  | Not started
M2 | 9 | 10 | Write S1 (A11, B5, B6, B8) + S4 estimated-GMV note | 3 |  | Not started
M3 | 1 | 1 | Detection SQL for A9 + B4 | 2 |  | Not started
M3 | 2 | 2 | Confirm A9; define B4 thresholds (≥0.75 / 0.65–0.75 / <0.65) | 1.5 |  | Not started
M3 | 3 | 3 | A9 canonical product rule (catalogue wins) | 2 |  | Not started
M3 | 4 | 4 | B4 match listings; write corrected silver_product_master | 3 |  | Not started
M3 | 5 | 5 | Rebuild dim_product (SCD2) | 2.5 |  | Not started
M3 | 6 | 6 | Check 3 grain on product-joined facts | 1 |  | Not started
M3 | 7 | 7 | vw_open_box_conversion_rate | 1.5 |  | Not started
M3 | 9 | 8 | Write S1 (A9, B4) + S2 dim_product rebuild note | 2 |  | Not started
M4 | 1 | 1 | Detection SQL for A6 + A10 | 2 |  | Not started
M4 | 2 | 2 | Confirm counts; note A7 vs A10 predicate distinction | 1 |  | Not started
M4 | 3 | 3 | A6 (qty→0 + oversell flag), A10 (correct condition to open-box) | 3 |  | Not started
M4 | 4 | 4 | Write corrected silver_si_inventory_snapshots + silver_rr_return_receipts | 1.5 |  | Not started
M4 | 5 | 5 | Rebuild dim_store + fact_warehouse_inventory_snapshot | 2.5 | Lead's A5/A7/A8 inventory corrections (shared inventory Silver) | Not started
M4 | 6 | 6 | Checks 4 (net=gross−disc−return) + 8 (inventory balance reconciliation) | 2.5 |  | Not started
M4 | 7 | 7 | Build your 6 inventory + BORIS views | 3.5 |  | Not started
M4 | 8 | 8 | Inventory Health page | 3 |  | Not started
M4 | 9 | 9 | Write S1 (A6, A10) + S2 inventory rebuild + S3 inventory checks | 2 |  | Not started
M5 | 1 | 1 | Detection SQL for A1, A2, A3 | 3 |  | Not started
M5 | 2 | 2 | Confirm A1/A2 counts + record the 94-vs-178 defence | 2 |  | Not started
M5 | 3 | 3 | A1 (zero cancelled revenue), A2 (flag reversal-required) | 2.5 |  | Not started
M5 | 3 | 4 | A3 normalise to tax-exclusive basis | 2 |  | Not started
M5 | 4 | 5 | Write corrected silver_ec_orders + silver_pos_transactions + returns | 1.5 | M2 (A11) + Lead (B1) corrections to silver_ec_orders must be merged first | Not started
M5 | 5 | 6 | Rebuild fact_ecommerce_order_line (keystone) + store-sale + return facts | 3.5 | M2 dim_customer rebuild (fact_ecommerce_order_line joins it) | Not started
M5 | 6 | 7 | Check 4 additive sanity (net=gross−disc−return) | 1 |  | Not started
M5 | 7 | 8 | Build the 6 Finance KPI views | 4 |  | Not started
M5 | 8 | 9 | Sales by Channel page | 3 |  | Not started
M5 | 9 | 10 | Write S1 (A1, A2, A3) + S4 GSV→NCR detail | 2.5 |  | Not started
M6 | 1 | 1 | Detection SQL for A4, A13, A15, A16 | 3 |  | Not started
M6 | 2 | 2 | Confirm counts + layer A13 multi-signal predicate | 2 |  | Not started
M6 | 3 | 3 | A4 (relabel ESTIMATED), A15 (verified_purchase=FALSE), A16 (dedupe canonical case) | 3 |  | Not started
M6 | 3 | 4 | A13 fraud-ring flag + risk tier | 2 |  | Not started
M6 | 4 | 5 | Write corrected silver_nl_listing_events, silver_rv_reviews, silver_cs_cases | 1.5 |  | Not started
M6 | 5 | 6 | Rebuild dim_seller, fact_customer_review, fact_classified_listing_event | 2.5 |  | Not started
M6 | 6 | 7 | Assist Check 9 (no ESTIMATED NL in confirmed totals) + Check 3 (grain) | 1.5 |  | Not started
M6 | 7 | 8 | Build the 4 ecommerce funnel views | 3 | Lead's clickstream fact rebuild (fact_web_session / fact_web_page_event) | Not started
M6 | 8 | 9 | Customer Journey page | 3 |  | Not started
M6 | 9 | 10 | Write S1 (A4, A13, A15, A16) + S2 review/listing rebuild | 2 |  | Not started

## KPI Views
KPI | View | Group | Owner | Certainty | View created | Validated | Status
Gross Sale Value | vw_gsv | Finance | M5 | CONFIRMED | No | No | Not started
Net Confirmed Revenue | vw_ncr | Finance | M5 | CONFIRMED | No | No | Not started
Revenue Leakage | vw_revenue_leakage | Finance | M5 | CONFIRMED | No | No | Not started
Gross Margin by Channel | vw_gross_margin_by_channel | Finance | M5 | CONFIRMED | No | No | Not started
Net Margin after Fulfilment | vw_net_margin_after_fulfilment | Finance | M5 | CONFIRMED | No | No | Not started
Confirmed GMV | vw_confirmed_gmv | Finance | M2 | CONFIRMED | No | No | Not started
Estimated Classified GMV | vw_estimated_classified_gmv | Finance | M2 | ESTIMATED | No | No | Not started
Campaign Incremental Revenue | vw_campaign_incremental_revenue | Finance | Lead | CONFIRMED | No | No | Not started
ATP by SKU-Location-Date | vw_atp_sku_loc_date | Inventory | M4 | CONFIRMED (semi-additive) | No | No | Not started
Stockout Rate | vw_stockout_rate | Inventory | M4 | CONFIRMED | No | No | Not started
Oversell Count | vw_oversell_count | Inventory | M4 | CONFIRMED | No | No | Not started
Inventory Accuracy Rate | vw_inventory_accuracy_rate | Inventory | M4 | CONFIRMED | No | No | Not started
Return-to-Restock Cycle Time | vw_return_to_restock_cycle_time | Inventory | M4 | CONFIRMED | No | No | Not started
Open-Box Conversion Rate | vw_open_box_conversion_rate | Inventory | M3 | CONFIRMED | No | No | Not started
Cart Abandonment Rate | vw_cart_abandonment_rate | Ecom/Store | M6 | CONFIRMED | No | No | Not started
Checkout Conversion Rate | vw_checkout_conversion_rate | Ecom/Store | M6 | CONFIRMED | No | No | Not started
Browse-Online-Buy-In-Store | vw_browse_online_buy_in_store_rate | Ecom/Store | M6 | INFERRED | No | No | Not started
Browse-Online-Contact-NexaLocal | vw_browse_online_contact_nexalocal_rate | Ecom/Store | M6 | INFERRED | No | No | Not started
BOPIS Pickup Readiness Time | vw_bopis_pickup_readiness_time | Ecom/Store | Lead | CONFIRMED | No | No | Not started
BORIS Count | vw_boris_count | Ecom/Store | M4 | CONFIRMED | No | No | Not started
On-Time Delivery Rate | vw_on_time_delivery_rate | Ecom/Store | Lead | CONFIRMED | No | No | Not started
Payment Failure Rate | vw_payment_failure_rate | Ecom/Store | M5 | CONFIRMED | No | No | Not started
Active Listing Count | vw_active_listing_count | NexaLocal/Seller | M2 | CONFIRMED | No | No | Not started
Listing Contact Rate | vw_listing_contact_rate | NexaLocal/Seller | M2 | CONFIRMED | No | No | Not started
Relisting Rate | vw_relisting_rate | NexaLocal/Seller | M2 | CONFIRMED | No | No | Not started
Duplicate Listing Inflation Factor | vw_duplicate_listing_inflation_factor | NexaLocal/Seller | M2 | CONFIRMED | No | No | Not started
Seller Risk Score Distribution | vw_seller_risk_score_distribution | NexaLocal/Seller | M2 | CONFIRMED | No | No | Not started
Validated Report Rate | vw_validated_report_rate | NexaLocal/Seller | M2 | INFERRED | No | No | Not started

## Validation
Check# | Name | Owner | Iter-1 result | Iter-2 result | Final result | Notes
1 | Completeness / row counts | Lead |  |  | Pending
2 | Referential Integrity (no orphan FKs) | Lead |  |  | Pending
3 | Grain Violations | M3 |  |  | Pending
4 | Additive Fact Sanity (net=gross-disc-return) | M5 / M4 |  |  | Pending
5 | Semi-Additive Guard (no SUM(ATP) across dates) | Lead |  |  | Pending
6 | Metric Certainty Completeness | M2 |  |  | Pending
7 | Campaign Period Coverage (>=1 row/fact) | Lead |  |  | Pending
8 | Inventory Balance Reconciliation | M4 |  |  | Pending
9 | Classified Certainty Segregation | M2 |  |  | Pending
10 | Temporal Consistency (delivered-after-shipped) | Lead |  |  | Pending

## Deliverables
Artifact | Path | Owner | Status
Written report (PDF) | report/nexamart_m2_report.pdf | Lead | Not started
Anomaly resolution notebook | notebooks/05_anomaly_resolution.ipynb | All (resolution owners) | Not started
Gold rebuild notebook | notebooks/06_gold_rebuild.ipynb | Lead + fact owners | Not started
Anomaly discovery SQL | sql/anomaly_discovery.sql | All | Not started
Anomaly resolution SQL | sql/anomaly_resolution.sql | All | Not started
Validation suite SQL | sql/validation_suite.sql | Lead | Not started
KPI views SQL | sql/kpi_views.sql | All (KPI owners) | Not started
Dashboard file (.pbix/.twbx) | dashboard/nexamart_dashboard.* | All (page owners) | Not started
Dashboard screenshots | dashboard/screenshots/ | All | Not started
Presentation (5-10 slides) | presentation/nexamart_m2_presentation.* | Lead | Not started
Submission ZIP | nexamart_m2_group_[N].zip | Lead | Not started

## Standup log
Date | Member | Yesterday | Today | Blockers